## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Team-3C
Testing Team Name

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper or U-Fund manager I want my username to be authorized by the server so that I can access the application. | Given that I am a U-Fund manager, when I log into the application, then I expect to see a curated dashboard for the admin role.
Given that I am a helper, when I log into the application, then I expect to see a curated dashboard for my specific helper account.
Given I log in with a username that does not exist, when I try and access the application, then it should create a new user for that username
Given I log in with no username, when I try and access the application, then it should deny access and return an appropriate error message
As a U-Fund Manager I want to see a list of needs in the needs cupboard so that I know which needs have been stored there. | Given I log into the application, when I am a U-Fund Manager, I expect to see a list of the needs in the cupboard
Given I log into the application as a U-Fund Manager, when there are no needs in the needs cupboard, I should expect to see an empty list.
As a U-fund Manager I want to remove needs from the needs cupboard so that I can choose which needs are no longer are being funded. | Given I am a U-Fund Manager, when I remove a need from the cupboard, then it should no longer be visible in the cupboard.
As a U-fund Manager I want to add needs to the needs cupboard so that they can be funded. | Given that I am a U-Fund Manager, when I add a need, then the helpers and I should be able to see the need in the cupboard.
As a U-fund Manager I want to edit the data of needs in the needs cupboard so that I can convey intended information to the helpers. | Given I am a U-Fund Manager, when I edit a need, then the information displayed for the need should be visibly updated.
As a Helper I want to see a list of needs so that I can choose which needs to contribute to. | Given that I am a Helper, when I log in with my username, I can see a list of needs that I can contribute to.
As a Helper I want to search for needs so that I can find a specific need easier. | Given that I am a Helper, when I have a need in mind and search it by name, then I see only the specific needs matching my search.
As a Helper I want to see my funding basket so that I can see the needs I have selected to fund. | Given I am a helper and my basket has needs in it, when I view my basket then I expect to see the needs that are in my basket.
Given I am a helper and my basket doesn't have needs, when I view my basket, then I expect to not see any needs.
As a Helper I want to check-out needs in my funding basket so that I can fund them. | Given that I am a helper, and I have added items to my basket, when I check out my basket, then it will update the quantity of a need in the cupboard and clear my basket.
Given I am a helper and I do not have any items in my basket, when I go to my basket page, then there should not be the option to check-out.
As a Helper I want to remove needs from my funding basket so that I can manage the contents of my funding basket. | Given I am a helper and I have items in my basket, when I go to my basket page and remove an item, then it should display the updated quanitity of the item in my basket.
Given I am a helper and I do not have any items in my basket, when I go to my basket page, there should not be the option to remove an item.
As a Helper I want to add needs to my funding basket so that I can fund them. | Given I am a helper, when I add a need from the cupboard to my basket, then it should display the item and its proper quantity under the items list in my basket.
Given I am a helper, when I add a need from the cupboard to my basket, then I should only be able to add copies of that need up to the quantity in the cupboard.
As a Helper I want to filter needs by type so that I can see needs of a specific type. | Given that I am a helper, when I search for a need in the cupboard and select the filter of a specific need type, then only the needs of that type should be shown in the cupboard.
As a Helper I want to be able to sign out so I can logout of the application when I am done. | Given that I am a Helper, when I log in with my username and want to logout, then I should be able to click the log out button and return to the login page.
As a Manager I want to be able to sign out so I can logout of the application when I am done. | Given that I am a Manager, when I log in with my username and want to log out, then I should be able to click log out button and return to the login page.
As a Helper I want to see a list of all previous transactions so that I can track which needs I’ve contributed to. | Given I am a helper, when I check-out and go the transaction history page, then I should be able to see the details of that transaction listed.
Given I am a helper, when I haven't made any purchases ever, then my transaction history should be empty.
As a Helper I want to filter needs by location so that I can see needs at a specific location. | Given I am a helper, when I search for needs in the cupboard and select the filter of a specific need location, then only the needs of that type should be shown in the cupboard.